## Dashboard
CONSTRUCTION PROJECT CONTROLS DASHBOARD
Project: | Riverside Mixed-Use ¦ Arlington, TX |  | Contract Value: | $2,400,000
Owner: | Riverside Development LLC |  | Report Date: | 2026-03-23
GC: | Suhas Ravi Construction Management |  | Project Phase: | Construction
KEY PERFORMANCE INDICATORS
KPI | Current | Target | Variance | Status
Cost Performance Index (CPI) | 1.0318 | ≥ 1.00 | 0.031762 | On Track
Schedule Performance Index (SPI) | 0.86518 | ≥ 1.00 | -0.13482 | At Risk
Budget Utilization (%) | 0.67885 | ≤ 85% | -0.17115 | Over Budget
Open RFIs | 5 | < 5 | 0 | Needs Attention
Submittals Overdue | 1 | 0 | 1 | Action Required
COST SUMMARY BY CSI DIVISION |  |  | SCHEDULE SUMMARY
CSI Division | Budget ($) | Actual ($) | Phase | Planned % | Actual %
01 - General Requirements | 100000 | 44200 | Site Preparation | 100% | 100%
02 - Existing Conditions | 45000 | 275000 | Foundation | 100% | 100%
03 - Concrete | 280000 | 93000 | Structural Frame | 100% | 95%
04 - Masonry | 95000 | 208000 | MEP Rough-In | 80% | 72%
05 - Metals | 210000 | 171000 | Exterior Envelope | 60% | 55%
06 - Wood & Plastics | 175000 | 127500 | Interior Rough-In | 40% | 35%
07 - Thermal & Moisture | 130000 | 143000 | Finishes | 5% | 3%
08 - Openings | 145000 | 48000 | Punch List/Closeout | 0% | 0%
09 - Finishes | 320000 | 12000 | 308000 | 3.75%
10-14 - Specialties/Equip | 180000 | 285000 | -105000 | 158.3%
21-23 - MEP Systems | 550000 | 149000 | 401000 | 27.09%
31-33 - Site Work | 150000 | 1673700 | -1523700 | 1116%
TOTAL | 2380000 | 3229400 | -919700 | 135.7%
Dashboard auto-updates when data is entered in Cost Tracker, Schedule, RFI Log, and Submittal Register tabs.

## Cost Tracker
COST TRACKER — RIVERSIDE MIXED-USE PROJECT
CSI Division | Original Budget ($) | Approved Change Orders ($) | Revised Budget ($) | Committed Cost ($) | Actual Cost to Date ($) | Estimated Cost at Completion ($) | Budget Remaining ($) | Cost Variance ($) | % Budget Spent | % Work Complete | Earned Value ($) | Cost Variance (EV) | CPI | SPI
01 - General Requirements | 120000 | 5000 | 125000 | 120360 | 118000 | 16.8571 | 124983.1429 | 7000 | 94.4% | 100% | 125000 | 7000 | 1.0593 | 1.0417
02 - Existing Conditions | 45000 | 0 | 45000 | 45084 | 44200 | 55.25 | 44944.75 | 800 | 98.22% | 100% | 45000 | 800 | 1.0181 | 1
03 - Concrete | 280000 | 12000 | 292000 | 280500 | 275000 | 24.6416 | 291975.3584 | 17000 | 94.18% | 98% | 286160 | 11160 | 1.0406 | 1.0429
04 - Masonry | 95000 | 2000 | 97000 | 94860 | 93000 | 45.1456 | 96954.8544 | 4000 | 95.88% | 98% | 95060 | 2060 | 1.0222 | 1.0211
05 - Metals | 210000 | 8000 | 218000 | 212160 | 208000 | 26.5985 | 217973.4015 | 10000 | 95.41% | 99% | 215820 | 7820 | 1.0376 | 1.0381
06 - Wood & Plastics | 175000 | 3500 | 178500 | 174420 | 171000 | 43.5115 | 178456.4885 | 7500 | 95.8% | 98% | 174930 | 3930 | 1.023 | 1.02
07 - Thermal & Moisture | 130000 | 1000 | 131000 | 130050 | 127500 | 144.8864 | 130855.1136 | 3500 | 97.33% | 98% | 128380 | 880 | 1.0069 | 1.0077
08 - Openings | 145000 | 4500 | 149500 | 145860 | 143000 | 28.5714 | 149471.4286 | 6500 | 95.65% | 99% | 148005 | 5005 | 1.035 | 1.031
09 - Finishes | 320000 | 6000 | 326000 | 48960 | 48000 | 53.3333 | 325946.6667 | 278000 | 14.72% | 15% | 48900 | 900 | 1.0188 | 1.0188
10-14 - Specialties/Equip | 180000 | 2500 | 182500 | 12240 | 12000 | 15.4839 | 182484.5161 | 170500 | 6.575% | 7% | 12775 | 775 | 1.0646 | 1.0139
21-23 - MEP Systems | 550000 | 18000 | 568000 | 290700 | 285000 | 27.5097 | 567972.4903 | 283000 | 50.18% | 52% | 295360 | 10360 | 1.0364 | 1.0327
31-33 - Site Work | 150000 | 3000 | 153000 | 151980 | 149000 | 60.3239 | 152939.6761 | 4000 | 97.39% | 99% | 151470 | 2470 | 1.0166 | 1.02
PROJECT TOTAL | 2400000 | 65500 | 2465500 | 1707174 | 1673700 | 542.1128 | 2464957.8872 | 791800 | 67.88% |  | 1726860 | 53160 | 1.0318 | 1.024
COLOR LEGEND: | Blue = Input cell (editable) |  | Green CPI/SPI = Performing well (≥ 1.00) |  |  | Red CPI/SPI = At risk (< 1.00)

## Schedule
SCHEDULE TRACKER — RIVERSIDE MIXED-USE PROJECT
Work Package | Planned Start | Planned Finish | Actual Start | Actual Finish | Duration (days) | Planned % Complete | Actual % Complete | Schedule Variance (days) | Status | Responsible Party | Notes | Float (days)
Site Mobilization & Prep | 1/6/2025 | 1/31/2025 | 1/6/2025 | 1/29/2025 | 25 | 100% | 100% | 0 | On Schedule | Turner CM | 0 | 1
Demolition & Excavation | 2/3/2025 | 2/28/2025 | 2/3/2025 | 3/3/2025 | 25 | 100% | 100% | 0 | On Schedule | Apex Demo | 0 | 1
Foundation — Footings & Grade | 3/3/2025 | 4/4/2025 | 3/5/2025 | 4/9/2025 | 32 | 100% | 100% | 0 | On Schedule | Concrete Plus | 0 | 1
Structural Steel Frame | 4/7/2025 | 5/16/2025 | 4/9/2025 | 5/19/2025 | 39 | 100% | 95% | -2 | Minor Delay | SteelCo | 2 | 0.95
Metal Deck & Concrete Slab | 5/19/2025 | 6/13/2025 | 5/21/2025 |  | 25 | 100% | 95% | -1 | Minor Delay | Concrete Plus | 1 | 0.95
Exterior Masonry & Envelope | 6/16/2025 | 8/8/2025 | 6/18/2025 |  | 53 | 80% | 72% | -4 | Minor Delay | MasonryPro | 15 | 0.9
Roofing System | 7/7/2025 | 8/1/2025 | 7/10/2025 |  | 25 | 90% | 82% | -2 | Minor Delay | RoofRight | 5 | 0.91111
Storefront & Glazing | 7/28/2025 | 8/22/2025 | 7/30/2025 |  | 25 | 70% | 62% | -2 | Minor Delay | GlassTech | 10 | 0.88571
MEP Rough-In — Electrical | 5/12/2025 | 8/22/2025 | 5/14/2025 |  | 72 | 75% | 68% | -5 | Minor Delay | ElecCo | 23 | 0.90667
MEP Rough-In — Plumbing | 5/12/2025 | 8/22/2025 | 5/14/2025 |  | 72 | 75% | 65% | -7 | Minor Delay | PlumbRight | 25 | 0.86667
MEP Rough-In — Mechanical | 5/26/2025 | 9/5/2025 | 5/28/2025 |  | 72 | 65% | 58% | -5 | Minor Delay | MechSystems | 30 | 0.89231
Drywall & Interior Framing | 8/11/2025 | 9/26/2025 | 8/14/2025 |  | 46 | 35% | 28% | -3 | Minor Delay | FramePro | 33 | 0.8
Painting & Wall Finishes | 9/15/2025 | 10/17/2025 |  |  | 32 | 10% | 5% | -2 | Minor Delay | PaintCo | 30 | 0.5
Flooring | 9/22/2025 | 10/24/2025 |  |  | 32 | 5% | 2% | -1 | Minor Delay | FloorCo | 31 | 0.4
Millwork & Casework | 9/29/2025 | 10/24/2025 |  |  | 25 | 5% | 2% | -1 | Minor Delay | MillCo | 25 | 0.4
FF&E Installation | 10/13/2025 | 11/7/2025 |  |  | 25 | 0% | 0% | 0 | On Schedule | Owner | 25 | 1
Site Utilities & Paving | 8/4/2025 | 9/5/2025 | 8/6/2025 |  | 32 | 85% | 80% | -2 | Minor Delay | CivilCo | 6 | 0.94118
Landscaping | 10/6/2025 | 10/31/2025 |  |  | 25 | 0% | 0% | 0 | On Schedule | GreenScape | 25 | 1
Final Inspections & Punch List | 11/3/2025 | 11/21/2025 |  |  | 18 | 0% | 0% | 0 | On Schedule | Turner CM | 18 | 1
Certificate of Occupancy | 11/24/2025 | 11/28/2025 |  |  | 5 | 0% | 0% | 0 | On Schedule | Turner CM | 5 | 1
PROJECT OVERALL | [5 empty] | 54.75% | 50.7% |  |  |  |  | 0.86518

## RFI Log
RFI LOG — RIVERSIDE MIXED-USE PROJECT
RFI # | Subject | Submitted By | Submitted To | Date Submitted | Date Required | Date Answered | Days Open | Priority | Status | Cost Impact ($) | Notes
RFI-001 | Footing depth conflict — grid line C vs structural dwg S2.1 | Suhas Ravi | Smith Structural Eng. | 1/22/2025 | 1/29/2025 | 1/27/2025 | 5 | High | Closed | 0 | Resolved — depth increased 6 in.
RFI-002 | Slab edge condition at north entry — see arch A3.4 | Concrete Plus | Smith Structural Eng. | 2/14/2025 | 2/21/2025 | 2/20/2025 | 6 | Med | Closed | 0 | Confirmed as drawn
RFI-003 | Column base plate anchor bolt pattern — grids B/3 | SteelCo | Smith Structural Eng. | 4/11/2025 | 4/18/2025 | 4/16/2025 | 5 | High | Closed | 2450 | Added 2 anchors per RFI response
RFI-004 | Exterior wall R-value — conflict between specs and energy calcs | MasonryPro | EnviroConsult | 6/20/2025 | 6/27/2025 | 6/25/2025 | 5 | Med | Closed | 0 | Spec takes precedence
RFI-005 | Roof drain size conflict — plbg P2.1 vs mech M3.2 | PlumbRight | EnviroConsult | 7/8/2025 | 7/15/2025 | 7/14/2025 | 6 | High | Closed | 1800 | Mechanical governs — 4 in. drain
RFI-006 | Storefront sill height at lobby — arch A5.2 dim unclear | GlassTech | Design Arch LLC | 7/31/2025 | 8/7/2025 |  | 235 | High | Open | 0 | Awaiting architect response
RFI-007 | Electrical panel location conflict with plumbing chase | ElecCo | MEP Coordinator | 8/1/2025 | 8/8/2025 |  | 234 | High | Open | 0 | OAC meeting 8/5 — decision pending
RFI-008 | Ceiling height at corridor 2B — conflicts between arch & struct | FramePro | Design Arch LLC | 8/4/2025 | 8/11/2025 |  | 231 | Med | Open | 0 | On hold pending BIM coordination
RFI-009 | Paint color spec — owner change request, lobby accent wall | PaintCo | Owner Rep | 8/5/2025 | 8/12/2025 |  | 230 | Low | Open | 0 | Owner to confirm selection
RFI-010 | Parking lot light pole base detail missing from civil drawings | CivilCo | Design Arch LLC | 8/6/2025 | 8/13/2025 |  | 229 | Med | Open | 0 | Issued for information only
Formulas:
Days Open = IF([Date Answered]<>"",[Date Answered]-[Date Submitted],TODAY()-[Date Submitted])

## Submittal Register
SUBMITTAL REGISTER — RIVERSIDE MIXED-USE PROJECT
Sub # | Description | Submitted By | Date Submitted | Date Required | Date Returned | Status | Return Code | Resubmittal Required? | Notes
S-001 | Concrete Mix Design — 4000 psi slab | Concrete Plus | 1/27/2025 | 2/3/2025 | 2/1/2025 | Approved | A | No | Approved as submitted
S-002 | Rebar Shop Drawings — foundations | Concrete Plus | 1/27/2025 | 2/3/2025 | 2/4/2025 | Approved | A | No | Minor note only
S-003 | Structural Steel Shop Drawings — frame | SteelCo | 3/10/2025 | 3/24/2025 | 3/21/2025 | Approved | A | No | Approved as submitted
S-004 | Metal Deck Shop Drawings | SteelCo | 3/17/2025 | 3/31/2025 | 3/28/2025 | Approved w/ Comments | B | No | Weld pattern revised
S-005 | Exterior Masonry — product data & samples | MasonryPro | 5/5/2025 | 5/19/2025 | 5/16/2025 | Approved | A | No | Color sample approved
S-006 | Roofing System — TPO product data | RoofRight | 5/19/2025 | 6/2/2025 | 6/3/2025 | Approved w/ Comments | B | No | Thickness confirmed
S-007 | Storefront System — shop drawings & data | GlassTech | 6/23/2025 | 7/7/2025 | 7/9/2025 | Revise & Resubmit | C | Yes | Anchor spacing non-compliant
S-008 | Storefront System — Resubmittal | GlassTech | 7/21/2025 | 8/4/2025 | 8/1/2025 | Approved | A | No | Resubmittal approved
S-009 | Electrical Switchgear — product data | ElecCo | 6/9/2025 | 6/23/2025 | 6/20/2025 | Approved | A | No | Long lead item confirmed
S-010 | HVAC Equipment Schedule — AHU data | MechSystems | 6/16/2025 | 6/30/2025 | 6/27/2025 | Approved w/ Comments | B | No | Filter spec upgraded
S-011 | Plumbing Fixtures — product data & samples | PlumbRight | 6/23/2025 | 7/7/2025 | 7/5/2025 | Approved | A | No | WaterSense fixtures confirmed
S-012 | Interior Doors & Hardware Schedule | FramePro | 7/14/2025 | 7/28/2025 |  | Pending | — | — | Submitted; under review
S-013 | Flooring — tile & carpet samples | FloorCo | 7/28/2025 | 8/11/2025 |  | Pending | — | — | Submitted; under review
S-014 | Paint Color Schedule — full palette | PaintCo | 8/4/2025 | 8/18/2025 |  | Pending | — | — | Pending owner confirmation
S-015 | Site Lighting — pole & fixture data | CivilCo | 8/4/2025 | 8/18/2025 |  | Overdue | — | — | Required by 8/18 — no submission

## S-Curve & Charts
S-CURVE — PLANNED VS ACTUAL COST CUMULATIVE
Period | Planned Cost ($) | Actual Cost ($) | Cumul. Planned ($) | Cumul. Actual ($)
Jan 2025 | 85000 | 82000 | 85000 | 82000
Feb 2025 | 110000 | 108000 | 195000 | 190000
Mar 2025 | 145000 | 143000 | 340000 | 333000
Apr 2025 | 165000 | 161000 | 505000 | 494000
May 2025 | 210000 | 198000 | 715000 | 692000
Jun 2025 | 230000 | 218000 | 945000 | 910000
Jul 2025 | 245000 | 228000 | 1190000 | 1138000
Aug 2025 | 260000 | 235000 | 1450000 | 1373000
Sep 2025 | 255000 |  | 1705000
Oct 2025 | 240000 |  | 1945000
Nov 2025 | 205000 |  | 2150000
Dec 2025 | 150000 |  | 2300000
Jan 2026 | 75000 |  | 2375000
Feb 2026 | 45000 |  | 2420000